## work done
id | sprint | status | resolution | project | story_points | work_done | planned
3656 | 1 | closed | fixed | Admin | 0 | 64.1 | 1
3638 | 1 | closed | fixed | Admin | 0 | 1 | 1
3636 | 1 | closed |  | Admin | 0 | 39 | 1
3644 | 1 | closed | fixed | Admin | 0 | 8.75 | 1
3652 | 1 | closed | fixed | Admin | 0 | 59 | 1
3650 | 1 | closed | fixed | Slytherin | 0 | 16 | 1
3648 | 1 | closed | fixed | Hufflepuff | 0 | 12.4 | 1
3646 | 1 | closed | fixed | Gryffindor | 0 | 3 | 1
3647 | 1 | closed | fixed | Gryffindor | 0 | 23.5 | 1
3651 | 1 | closed | fixed | Operation | 0 | 4.75 | 1
3640 | 1 | closed | fixed | Operation | 0 | 71.75 | 1
3649 | 1 | closed | fixed | Ravenclaw | 0 | 11 | 1
3808 | 2 | closed | fixed | Gryffindor | 0 | 12.3 | 1
3807 | 2 | closed | fixed | Admin | 0 | 75.5 | 1
3798 | 2 | closed | fixed | Admin | 0 | 14.3 | 1
3784 | 2 | closed | fixed | Admin | 0 | 57.4 | 1
3924 | 2 | closed | fixed | Gryffindor | 0 | 4 | 1
3794 | 2 | closed | fixed | Operation | 0 | 25.5 | 1
3809 | 2 | closed | wontfix | Hufflepuff | 0 | 0 | 1
3792 | 2 | closed | fixed | Admin | 0 | 3.4 | 1
3804 | 2 | closed | fixed | Admin | 0 | 1.5 | 1
3767 | 2 | closed | fixed | Admin | 0 | 22 | 1
3803 | 2 | closed |  | Slytherin | 0 | 10.8 | 1
3801 | 2 | closed | fixed | Hufflepuff | 0 | 10 | 1
3790 | 2 | closed | fixed | Admin | 0 | 30.5 | 1
3800 | 2 | closed | fixed | Gryffindor | 0 | 14 | 1
3802 | 2 | closed | fixed | Ravenclaw | 0 | 9 | 1
3955 | 3 | new |  | Admin | 0 | 13.5 | 1
3961 | 3 | closed | fixed | Admin | 0 | 62.2 | 1
3947 | 3 | closed |  | Admin | 0 | 37.5 | 1
4098 | 3 | closed | fixed | Hufflepuff | 0 | 5 | 1
3957 | 3 | closed | fixed | Hufflepuff | 0 | 6 | 1
4092 | 3 | closed |  | Operation | 0 | 2 | 1
3978 | 3 | new |  | Admin | 0 | 60.5 | 1
3959 | 3 | new |  | Ravenclaw | 0 | 6 | 1
3953 | 3 | new |  | Admin | 0 | 3.6 | 1
4069 | 3 | new |  | Gryffindor | 0 | 8.5 | 1
3949 | 3 | accepted |  | Operation | 0 | 61.5 | 1
3628 | 1 | closed | fixed | Gryffindor | 1 | 36 | 1
3589 | 1 | closed | fixed | Gryffindor | 8 | 162.9 | 1
3660 | 3 | closed | fixed | Slytherin | 8 | 158.4 | 1
3591 | 2 | closed | fixed | Hogsmeade | 1 | 19 | 1
3899 | 3 | closed | fixed | ShriekingShack | 1 | 9.5 | 0
3590 | 2 | closed | fixed | Gryffindor | 5 | 86 | 1
3621 | 3 | closed | fixed | Hufflepuff | 1 | 17 | 1
3623 | 2 | closed | fixed | Gryffindor | 5 | 82.5 | 1
528 | 1 | closed | fixed | Improvements | 3 | 44 | 1
3936 | 3 | closed | fixed | Gryffindor | 5 | 62.5 | 0
3601 | 3 | closed | fixed | Ravenclaw | 3 | 36 | 1
3578 | 3 | closed | fixed | Ravenclaw | 1 | 11.5 | 1
3613 | 3 | closed | fixed | Hufflepuff | 3 | 32 | 1
3565 | 2 | closed | fixed | Operation | 2 | 19.5 | 0
3627 | 1 | closed | fixed | Gryffindor | 1 | 9.25 | 1
3931 | 2 | closed | fixed | Improvements | 1 | 9 | 1
3632 | 2 | closed | fixed | Gryffindor | 13 | 111.5 | 1
3945 | 3 | closed |  | Improvements | 1 | 8.5 | 1
3631 | 1 | closed | fixed | Gryffindor | 5 | 42 | 1
3946 | 3 | closed | fixed | Gryffindor | 2 | 15.5 | 1
3607 | 3 | closed | fixed | Gryffindor | 3 | 23 | 1
3606 | 3 | closed | fixed | Gryffindor | 8 | 61 | 1
3908 | 3 | closed | fixed | Hufflepuff | 2 | 15 | 1
3605 | 3 | closed | fixed | Gryffindor | 5 | 37 | 1
3773 | 3 | closed | fixed | Slytherin | 2 | 14.5 | 1
3568 | 3 | closed | fixed | Operation | 5 | 36 | 0
3609 | 3 | closed | fixed | Hufflepuff | 8 | 57.5 | 1
3635 | 1 | closed | fixed | Operation | 1 | 7 | 1
3917 | 3 | closed | fixed | Hufflepuff | 1 | 7 | 1
4072 | 3 | new |  | Gryffindor | 0 | 32 | 1
3776 | 2 | closed | fixed | Gryffindor | 3 | 19 | 1
4062 | 3 | new |  | Ravenclaw | 0 | 8 | 1
4061 | 3 | new |  | Slytherin | 0 | 6.5 | 1
4090 | 3 | new |  | Slytherin | 0 | 5.75 | 1
4076 | 3 | closed |  | Hogsmeade | 0 | 1.5 | 1
3581 | 2 | closed | fixed | Ravenclaw | 5 | 30.5 | 1
3909 | 3 | closed | fixed | Hufflepuff | 3 | 18.25 | 1
3543 | 1 | closed | fixed | Operation | 3 | 18 | 0
3898 | 3 | closed | fixed | ChangeRequest | 1 | 6 | 0
3905 | 3 | closed | fixed | Gryffindor | 1 | 6 | 0
3633 | 2 | closed | fixed | Gryffindor | 13 | 77.2 | 1
3612 | 2 | closed | fixed | Hufflepuff | 8 | 47 | 1
3967 | 3 | closed | fixed | ShriekingShack | 2 | 11.5 | 1
3906 | 3 | closed | fixed | Gryffindor | 3 | 16 | 0
3770 | 3 | closed | fixed | Slytherin | 5 | 23 | 1
3777 | 1 | closed | fixed | Hufflepuff | 5 | 22.5 | 1
3428 | 1 | closed | fixed | Improvements | 13 | 57.5 | 1
3604 | 2 | closed | fixed | Gryffindor | 3 | 13.1 | 1
3547 | 1 | closed | fixed | Operation | 8 | 34.5 | 0
3293 | 3 | closed |  | Improvements | 2 | 8.25 | 1
3937 | 3 | closed | fixed | Slytherin | 5 | 16.5 | 1
3966 | 3 | closed | fixed | ShriekingShack | 2 | 6 | 1
3554 | 2 | closed | fixed | Operation | 8 | 23 | 1
3625 | 3 | closed | fixed | Gryffindor | 3 | 6.5 | 1
3037 | 2 | closed | fixed | Slytherin | 13 | 14.05 | 1